## High Level Plan
Environment | Need to Complete by | Task | Data Center | schema | Owner Team | Performed By
Erwin | Completed | Model Changes | na |  | DA | Bee
dev9 |  | Convert Tables to Partitions | Teramark | eps_owner_fmdev9_eps3 | DBA | Venu
dev9 |  | Review Changes- validate | Teramark | eps_owner_fmdev9_eps3 | DBA | Jonas
Imp1b | Completed | create data scripts for new column Data | hp | eps_owner | DA/DBA | Jonas
imp1b | 2015-09-29 | Implement all Partition changes | HP | eps_owner | DBA/DA | Venu/Jonas
Impl0/Test0 | Completed | create data scripts for new column Data | hp | eps_owner | DA/DBA | Jonas
impl0/test0 |  | Implement all Partition changes | HP | eps_owner | DBA/DA | Venu/Jonas
Prod | Completed | create data scripts for new column Data | hp | eps_owner | DA/DBA | Jonas
Prod | 2015-09-04 | Implement all Partition changes | HP | eps_owner | DBA/DA | Venu/Jonas
Prod-r | Completed | create data scripts for new column Data | hp | eps_owner | DA/DBA | Jonas
Prod-r | 2015-09-18 | Implement all Partition changes | HP | eps_owner | DBA/DA | Venu/Jonas

## Partition Requirements_earl
NEW COLUMNS | PARTITIONING | Reference Partition Children to Parent Policy Version | Reference Partition on the following child tables to parent PolicyMemberVersion | Policypaymenttrans
PolicyMemberVersion: Add new column PolicyStartDate | PolicyMemberVersion, PolicyMember, PolicyVersion will be partitioned by subscriberStateCd and Subpartitioned by Year in eligibilityBeginDate | PolicyStatus and PolicyPremium | POLICYMEMBERSTATUS
PolicyMember: Add new column subscriberStateCd & PolicyStartDate |  |  | POLICYMEMBERLANGUAGEABILITY
PolicyVersion: No new columns needed |  |  | POLICYMEMBERTELEPHONE
POLICYMEMBERADDRESS
DA will provide these changes to DBA |  |  | POLICYMEMBERMAINTTYPEREASON
POLICYMEMBERPREMIUM
POLICYMAINTENANCETYPEREASON
MEMBERPOLICYRACEETHNICITY
Currently, we have policyStartDate, benefitBeginDate on the db. As part of pp8, |  |  | POLICYMEMBEREMAILADDRESS
1. PolicyStartDate renamed -> eligibilityBeginDate
2. BenefitBeginDate renamed -> policyStartDate

## Imp_details_old way
ACTIVITY | Description | Performed by | Script created Dynamic or In Advance | Status HPDEV1 | TEST2 | IMPL1A | IMPL1B | IMPL2
PREPARATION
Get an account request to HP for eps_owner_part | This is the baseline account for holding the current DDL completely | DA - Jonas | In Advance | done in hptest2 and
create loopback database on eps_owner_part | We want the loopback database link to reference the source schema eps_owner. | DA - Jonas | In Advance
Check the names of all columns subscriber state cd for the tables being partitioned. | Verify the partition keys | DA - Jonas | In Advance
import eps_owner to eps_owner_part | Create a baseline for eps_owner | CGI
EXTRACT eps_owner to DDL checking off the following options in sqldeveloper: export DDL, grants, Terminator, storage, terminator, pretty print, add force to views, ADD BYTE. On the objects choice list, toggle all. Do this only for the Tables in Blue Below ('POLICYMEMBERSTATUS', 'POLICYMEMBERLANGUAGEABILITY', 'POLICYMEMBERTELEPHONE', 'POLICYMEMBERADDRESS', 'POLICYMEMBERVERSION', 'POLICYMEMBERMAINTTYPEREASON', 'POLICYMEMBERPREMIUM', 'POLICYMAINTENANCETYPEREASON', 'MEMBERPOLICYRACEETHNICITY', 'POLICYMEMBEREMAILADDRESS', 'POLICYMEMBER', 'POLICYVERSION', 'POLICYSTATUS', 'POLICYPREMIUM') | We need to get a script to be used as the basis for adding all the details back. Save this as all_earl_ddl.sql | DA | Dynamic
Extract ddl with script part_metadata_extract.sql | Creates the DDL for the main tables
Extract only tables, indexes, constraints for
Create the partitioning clause to be used with all tables being partitioined by state. Target Tables are PolicyMemberVersion, PolicyMember, PolicyVersion | WE want to have a quick and easy partition clause on hand to adapt to the small subset of the Extracted DDL | DA - Jonas | In Advance
create the Reference partitioning clause for the children referencing POLICYVERSION for tables PolicyStatus and PolicyPremimium | WE want to have a quick and easy partition clause on hand to adapt to the small subset of the Extracted DDL | DA - Jonas | In Advance
Create the reference partitioning clause refeferencing POLICYMEMBERVERSION for the children POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS | WE want to have a quick and easy partition clause on hand to adapt to the small subset of the Extracted DDL | DA - Jonas | In Advance
Create a separate partitioning DDL using the extracted DDL to rebuild the targed tables as a partitioned table by putting the PK constraint, THE PK Index and the partitioning clause place as well as the child tables. Include enable row movement clause | Adapt the extracted DDL specific to the tables from the extraction DDL | DA Jonas | Dynamic
Create Script part_rename_tables.sql to rename tables to their currentname_T For example, rename table NADINE to NADINE_T. Tables are in blue below: POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMemberVersion, PolicyMember, PolicyVersion PolicyStatus PolicyPremimium | Need to rename current tables to be backup tables. Rename table_name to table_name_T | DA-Nadene | In Advance
Create a script called part_copy_data.sql to copy the data back for each table tablename_T to tablename in parallel - do not use the append hint unless it's right before the next full backup. Bases script on tables in blue below:POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMemberVersion, PolicyMember, PolicyVersion PolicyStatus PolicyPremimium | Script to copy data back from renamed tables to new partitioned tables. Insert into tablename select * from tablename_t; | DA - Nadene | In Advance
Create a sql generating sql called part_drop_cons .sql cons.sql to drop constraints cascade for all tables being rebuilt in blue below and append a "_T" to the table names below as part of the generated SQL. use the cascade option POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMember, PolicyVersion PolicyStatus PolicyPremimium | sql generating sql script to drop all constraints and constraints. We will only run this if we can't rename and disable constraints. Alter table xxx drop constraint constraint_name cascade;. . | DA - Nadene | In Advance
Create a sql generating sql called part_drop_ind .sql cons.sql to drop indexes for all tables being rebuilt in blue below and append a "_T" to the table names below as part of the generated SQL. POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMember, PolicyVersion PolicyStatus PolicyPremium | sql generating sql script to drop all indexes. We will only run this if we cannot rename and disable indexes. Drop index indexname; | DA - Nadene | In Advance
Create a sql generating sql called part_rename_cons.sql to disable and rename constraints from constraintname to constraintname_T for tables below these are actually two seperate commands . The sql generating sql should append a "_T" also at the end of each table_name. When disabling constraints use the cascade option. being rebuilt in blue below POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMember, PolicyVersion PolicyStatus PolicyPremium | sql generating sql script to rename constraints Alter table xxx rename constraint to constraint_T; | DA - Nadene | In Advance
Create a sql generating sql called part_disable_cons.sql to disable constraints with the assumption the tables already have a _T at tne end since they would already be renamed during implementaton. Thus the sql generating sql should append a "_T" also at the end of each table_name when generting the sql to be executed by the DBA. You are building these scripts in advance the actual table names don't exist with a "_T" yet. When disabling constraints use the cascade option. being rebuilt in blue below POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMember, PolicyVersion PolicyStatus PolicyPremimium | sql generating sql script to disable constraints. Alter table xxx modify constraint constraintname disable cascade;. ( PK indexes built on the constraint will disappear autmatically. They also reappear on constraint enabling). | DA - Nadene | In Advance
Create a sql generating sql called part_rename_ind.sql to Rename indexname to indexname_T do for tables below - these are actually two seperate commands and append a "_T" to the table names below: being rebuilt in blue below POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMember, PolicyVersion PolicyStatus PolicyPremium | sql generating sql script to rename indexes. Alter index xxxx to xxxx_T | DA - Nadene | In Advance
Create a sql generating sql script to drop all tables listed below with _T added POLICYMEMBERSTATUS POLICYMEMBERLANGUAGEABILITY POLICYMEMBERTELEPHONE POLICYMEMBERADDRESS POLICYMEMBERVERSION POLICYMEMBERMAINTTYPEREASON POLICYMEMBERPREMIUM POLICYMAINTENANCETYPEREASON MEMBERPOLICYRACEETHNICITY POLICYMEMBEREMAILADDRESS PolicyMemberVersion, PolicyMember, PolicyVersion PolicyStatus PolicyPremimium | drop table xxx cascade constraints; | DA-Nadene | Dynamic
IMPLEMENTATION
Create a baseline schema into eps_owner_part with impdp with no data selected with network link with defined loopback | Create a DDL Baseline in eps_owner_part | CGI
Confirm with sqldeveloper compare, that everything matches | Validate our baseline is correct with eps_owner | CGI | dynamic
Run part_rename_tables.sql | Rename the original tables to temporary tables | CGI | In Advance
Run Part_disable_cons.sql sql generating sql script to rename constraints and disable as well | We need to disable constraints. | CGI | dynamic
Run Part_rename_cons.sql sql generating sql script to rename constraints and disable as well | We need to rename constraints to tempoary constraint names…this is ok with constrraints disabled. | CGI | dynamic
Run Part_rename_ind.sql sql generating sql script to rename indexes. | We need to rename indexes to temporary names | CGI | dynamic
ONLY IF ISSUES WITH PART_RENAME_IND_CONS .SQL - OTHERWISE DON'T DO THIS…..Run Part_drop_ind.sql sql generating sql script to drop all indexes and drop all contraints cascade. | Dropping all constraints and indexes from the temp tables. | DA | Dynamic
Create script part_build_tables_basics.sql from the extracted DDL | This script will build the basic tables with PK/UK constraints and indexes and reference constraints specific to the partitioning clause only | DA | Dynamic
Create script part_build_remainder.sql with indexes in parallel nologging and constraints as no validate | This script is the remainder of the extracted DDL without the commands in part_tables_basics.sql | DA | dynamic
Run part_build_tables_basics.sql | Builds the partitioned tables in basic form. | CGI | dynamic
alter session force parallel 4; alter session force parallel query parallel 4; | Set the session to have parallel enabled. | CGI | Dynamic
Run part_copy_data.sql | Copies the data into the new partitioned scripts | CGI | In Advance
Run part_build_remainder.sql | Build the rest of the dependencies. | CGI | dynamic
run sqldeveloper compare to eps_owner and baseline (minus partitioning selection) to ensure all functionality is enabled. | Validate that schema is correct relative to functionality of objects in place | CGI | dynamic
Pending the change schedule we will try to peform as much of this in advance of deployment as possible

## CGIACCDBA PARTIONING DETAILS
ACTIVITY | Description | Performed by | Script created Dynamic or In Advance | Status HPDEV1 | TEST2 | IMPL1A | IMPL1B | IMPL2
PREPARATION
Confirm eps_owner_part exists and that it and eps_owner have privs as follows:• grant read/write on directory appl_db_dir and data_pump_dir • SELECT_CATALOG_ROLE , • CREATE INDEXTYPE • CREATE DATABASE LINK • CREATE MATERIALIZED VIEW • CREATE JOB • CREATE TRIGGER • CREATE PROCEDURE • CREATE SYNONYM • CREATE TYPE • CREATE TABLE • IMPORT FULL DATABASE • CREATE SEQUENCE • CREATE VIEW • UNLIMITED TABLESPACE - execute on dbms_metadata - execute on dbmd_redefinition ability to query dba_redefinition_errors | This is the baseline account for holding the current DDL completely | DBA/DA - Jonas | In Advance | done in hptest2 and
create loopback database link on eps_owner_part | We want the loopback database link to reference the source schema eps_owner. | DBA/DA - Jonas | In Advance
import eps_owner to eps_owner_part | Create a baseline for eps_owner | CGI
IMPLEMENTATION
DBA will create a flashback restore point FOR ROLLBACK | This is an easy method to account for rolling back | HP | dynamic
Create a baseline schema into eps_owner_part with impdp with no data selected with network link with defined loopback | Create a DDL Baseline in eps_owner_part | CGI | cgi
Confirm with sqldeveloper compare, that everything matches | Validate our baseline is correct with eps_owner | cgi/da | dynamic
Run partitioning_policymember.sql | partioning with dbms_redefinition - check for errors in dba_redefinition_errors after bringing in dependents | CGI | In Advance
Run partitioning_policyversion.sql | partioning with dbms_redefinition - check for errors in dba_redefinition_errors after bringing in dependents | CGI | In Advance
Run partitioning_policymemberversion.sql | partioning with dbms_redefinition - check for errors in dba_redefinition_errors after bringing in dependents | CGI | In Advance
Run Partioniong_policypaymenttrans.sql | partioning with dbms_redefinition - check for errors in dba_redefinition_errors after bringing in dependents | CGI | In Advance
run sqldeveloper compare to eps_owner and baseline (minus partitioning selection) to ensure all functionality is enabled. | Validate that schema is correct relative to functionality of objects in place | CGI | dynamic
Drop all temporary tables | CGI
gather statistics - run partitioning_gather_stats.sql | stats for the partitions
Pending the change schedule we will try to peform as much of this in advance of deployment as possible

## Rollback
Flashback to restore point.

## general questons
LOE Tasks | Owner | Environment | TableName
Data Volumes | DBA | hpdev1
impl1b
prod-r
prod
Starting Points | Jonas/DA | State Codes: ALL States ( state_configuration) | state_configuration (eps_owner)
| Jonas/DA | The oldest set of Data for policystartdate for partition starting points | 2009?
| Jonas/DA | Baseline of what changes will be in production on September 4 for tables being partitioned | ? - Reference schema to use
| jonas/DA | all states built up front - put in 7 years of part/subpart capability (state configuration table has all states). | yes
LOE Questions | Jonas/DA/DBA | Should we have Default partitions - no errors | no issues
| Jonas/DA/DBA | Global versus local indexes | Local except PK
| Jonas/DA/DBA | Split verus Add Partitions | Split the Default
| Jonas/DA/DBA | Question - how will we add the sub-partitions with - requirement jobs… | Split the Default
| Jonas/DA/DBA | Interval Partitions? Jonas to confirm if the app is using dates in it's queries as well - no list and interval | Should use - but…not guaranteed
| Jonas/DA/DBA | Interval-List Versus List Range? - can we save maintenance work with another job | Interval is very interesting
| Jonas/DA/DBA | App Requirements: Reporting on State and/or policystartdate | State for sure
| Jonas/DA/DBA | App Requirements: Inserting data based on state and policystartdate.
| Jonas/DA/DBA | App Requirements: Do you need all states without Dates. | Yes
| Jonas/DA/DBA | Interval-List impact on Archiving….example…drop 2003 in year 2015…this will drop all the states. | dropping dates is easier…
| Jonas/DA/DBA | Interval well tested on 11g as per DBA | no issues
| Jonas/DA/DBA | Go back to Bee - why is policystartdate nullable in some cases? | should not be ever. Bee will resolve
| Girish | Provide some sample queries to the team.
DBA | Partitition Job maintenance | Will depend on the answers to the partition management methods above.
Jonas |  |  | check on batchtransmsg

## Partition Requirments Payments
POLICYPAYMENTTRANS